## Team1_Estimated_Effort
Task Name: (Dependencies top to bottom) | [8 empty] | Alex | Edward | Colin | Liz | James H | James T | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task | By Task | By Task
Preliminary &
Parallel Tasks | Architecture |  |  |  |  | 10 |  | 10
|  | Design architecture | Project Manager | Alex | 10 |  | 10 |  | 10 | 0 | 0 | 0 | 0 | 0 | 10
| Requirements |  |  |  |  | 9 |  | 9
|  | Gather | Requirements Engineer | James H | 2 |  | 2 |  | 0 | 0 | 0 | 0 | 2 | 0 | 2
|  | Analyze | Requirements Engineer | James H | 4 |  | 4 |  | 0 | 0 | 0 | 0 | 4 | 0 | 4
|  | Specify | Requirements Engineer | James H | 3 |  | 3 |  | 0 | 0 | 0 | 0 | 3 | 0 | 3
| Documentation |  |  |  |  | 28 |  | 76
|  | Project Charter | Project Manager | Alex, James T | 2 |  | 4 |  | 2 | 0 | 0 | 0 | 0 | 2 | 4
|  | Release Plan | Project Manager | Alex, James T | 2 |  | 4 |  | 2 | 0 | 0 | 0 | 0 | 2 | 4
|  | Requirements Document | Project Manager, Requirements Engineer | Alex, James H | 5 |  | 10 |  | 5 | 0 | 0 | 0 | 5 | 0 | 10
|  | Project Plan | Project Manager, Developers | Alex, Edward, Liz, Colin, James H, James T | 5 |  | 30 |  | 5 | 5 | 5 | 5 | 5 | 5 | 30
|  | Architecture Document | Architect | Alex, James T | 4 |  | 8 |  | 4 | 0 | 0 | 0 | 0 | 4 | 8
|  | Test Report | Tester | Liz, Colin | 8 |  | 16 |  | 0 | 0 | 8 | 8 | 0 | 0 | 16
|  | User Guide & System Admin Doc | Developers, Requirements Engineer | Liz, Colin | 2 |  | 4 |  | 0 | 0 | 2 | 2 | 0 | 0 | 4
Coding | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Iteration 1: | Development |  |  |  |  | 41 |  | 69
|  | Determine technology needs | Developer | Alex, James T | 1 |  | 2 |  | 1 | 0 | 0 | 0 | 0 | 1 | 2
|  | Research and learn new language and environment | Developer | Edward, Liz, Colin, James H, James T | 10 |  | 50 |  | 0 | 10 | 10 | 10 | 10 | 10 | 50
|  | Set up SQL database | Developer | James H, Edward | 5 |  | 10 |  | 0 | 5 | 0 | 0 | 5 | 0 | 10
|  | Write basic queries | Developer | James H, Edward | 2 |  | 4 |  | 0 | 2 | 0 | 0 | 2 | 0 | 4
|  | Implement database | Developer | James H, Edward | 5 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Create HTTP handling code | Developer | Alex | 8 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Implement classes | Developer | Edward | 2 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Implement Front-End | Developer | Alex, James T | 6 |  | 3 |  | 3 | 0 | 0 | 0 | 0 | 0 | 0
|  | Unit Testing | Developer | Liz, Colin | 2 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Analysis |  |  |  |  | 6 |  | 0
|  | System Testing | Tester | Liz, Colin | 2 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Bug fix as required | Tester, Developer | Alex, James T | 2 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Evaluate needs for next iteration | Project Manager | James T | 2 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total |  |  |  |  | 94 | 94 | 164 | 164 | 32 | 22 | 25 | 25 | 36 | 24 | 164