## Team1_Estimated_Effort
Task Name: (Dependencies top to bottom) | [8 empty] | Alex | Edward | Colin | Liz | James H | James T
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task | By Task | By Task
Preliminary &
Parallel Tasks | Architecture |  |  |  |  | 10 |  | 1
|  | Design architecture | Project Manager | Alex | 10 |  | 1 |  | 1 | 0 | 0 | 0 | 0 | 0
| Requirements |  |  |  |  | 9 |  | 3
|  | Gather | Requirements Engineer | James H | 2 |  | 1 |  | 0 | 0 | 0 | 0 | 1 | 0
|  | Analyze | Requirements Engineer | James H | 4 |  | 1 |  | 0 | 0 | 0 | 0 | 1 | 0
|  | Specify | Requirements Engineer | James H | 3 |  | 1 |  | 0 | 0 | 0 | 0 | 1 | 0
| Documentation |  |  |  |  | 28 |  | 14
|  | Project Charter | Project Manager | Alex, James T | 2 |  | 2 |  | 1 | 0 | 0 | 0 | 0 | 1
|  | Release Plan | Project Manager | Alex, James T | 2 |  | 2 |  | 1 | 0 | 0 | 0 | 0 | 1
|  | Requirements Document | Project Manager, Requirements Engineer | Alex, James H | 5 |  | 1 |  | 1 | 0 | 0 | 0 | 1 | 0
|  | Project Plan | Project Manager, Developers | Alex, Edward, Liz, Colin, James H, James T | 5 |  | 4 |  | 1 | 1 | 0 | 0 | 1 | 1
|  | Architecture Document | Architect | Alex, James T | 4 |  | 2 |  | 1 | 0 | 0 | 0 | 0 | 1
|  | Test Report | Tester | Liz, Colin | 8 |  | 2 |  | 0 | 0 | 1 | 1 | 0 | 0
|  | User Guide & System Admin Doc | Developers, Requirements Engineer | Liz, Colin | 2 |  | 1 |  | 0 | 0 | 1 | 1 | 0 | 0
Coding | [6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | 0
Iteration 1: | Development |  |  |  |  | 41 |  | 23
|  | Determine technology needs | Developer | Alex, James T | 1 |  | 2 |  | 1 | 0 | 0 | 0 | 0 | 1
|  | Research and learn new language and environment | Developer | Edward, Liz, Colin, James H, James T | 10 |  | 5 |  | 0 | 1 | 1 | 1 | 1 | 1
|  | Set up SQL database | Developer | James H, Edward | 5 |  | 2 |  | 0 | 1 | 0 | 0 | 1 | 0
|  | Write basic queries | Developer | James H, Edward | 2 |  | 2 |  | 0 | 1 | 0 | 0 | 1 | 0
|  | Implement database | Developer | James H, Edward | 5 |  | 5 |  | 0 | 3 | 0 | 0 | 2 | 0
|  | Create HTTP handling code | Developer | Alex | 8 |  | 1 |  | 1 | 0 | 0 | 0 | 0 | 0
|  | Implement classes | Developer | Edward | 2 |  | 1 |  | 0 | 1 | 0 | 0 | 0 | 0
|  | Implement Front-End | Developer | Alex, James T | 6 |  | 3 |  | 2 | 0 | 0 | 0 | 0 | 1
|  | Manual Testing | Developer | Liz, Colin | 2 |  | 2 |  | 0 | 0 | 1 | 1 | 0 | 0
| Analysis |  |  |  |  | 6 |  | 31
|  | System Testing | Tester | Liz, Colin | 2 |  | 2 |  | 0 | 0 | 1 | 1 | 0 | 0
|  | Bug fix as required | Tester, Developer | Alex, James T | 2 |  | 4 |  | 1 | 1 | 0 | 0 | 1 | 1
|  | Evaluate needs for next iteration | Project Manager | James T | 2 |  | 1 |  | 0 | 0 | 0 | 0 | 0 | 1
Iteration 2: | Design |  |  |  |  | 13 |  | 11
|  | Implement any design changes | Project Manager | Alex, James T | 2 |  | 2 |  | 1 | 0 | 0 | 0 | 0 | 1
|  | Risk analysis | Project Manager | James Ta, Jingfan Bai | 2 |  | 2 |  | 0 | 0 | 0 | 1 | 0 | 1
|  | Final Design of Database | Developer | James H, Edward | 2 |  | 2 |  | 0 | 1 | 0 | 0 | 1 | 0
|  | Final interfacing design for database | Developer | James H, Edward | 5 |  | 3 |  | 0 | 2 | 0 | 0 | 1 | 0
|  | Design final UI for setting/transactions and landing page | Developer | Alex | 2 |  | 2 |  | 2 | 0 | 0 | 0 | 0 | 0
| Development |  |  |  |  | 30 |  | 12
|  | Implement Expanded database | Developer | James H, Edward | 10 |  | 3 |  | 0 | 2 | 0 | 0 | 1 | 0
|  | Implement final database interfacing | Developer | James H, Edward | 5 |  | 3 |  | 0 | 2 | 0 | 0 | 1 | 0
|  | Implement new settings/transactions page | Developer | Alex, James T | 5 |  | 2 |  | 1 | 0 | 0 | 0 | 0 | 1
|  | Implement new landing page | Developer | Alex, James T | 8 |  | 2 |  | 1 | 0 | 0 | 0 | 0 | 1
|  | Unit Testing | Developer | Liz, Colin | 2 |  | 2 |  | 0 | 0 | 1 | 1 | 0 | 0
| Analysis |  |  |  |  | 9 |  | 9
|  | System Testing | Tester | Liz, Colin | 5 |  | 2 |  | 0 | 0 | 1 | 1 | 0 | 0
|  | Bug fix as required | Tester, Developer | Alex, James T | 2 |  | 2 |  | 1 | 0 | 0 | 0 | 0 | 1
|  | Evaluate needs for next iteration | Project Manager | Liz, Colin | 2 |  | 5 |  | 0 | 0 | 3 | 2 | 0 | 0
Iteration 3: | Design |  |  |  |  | 11 |  | 9
|  | Implement any design changes | Project Manager | Alex, James T | 2 |  | 2 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Restrict new account creation to admins | Developer | James H, Alex | 2 |  | 2 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Final tweaks to database | Developer | James H, Edward | 5 |  | 3 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Further adjust Account Settings UI | Developer | Alex | 2 |  | 2 |  | 0 | 0 | 0 | 0 | 0 | 0
| Development |  |  |  |  | 20 |  | 9
|  | Stress test database | Developer | James H, Edward | 5 |  | 3 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Refactor "Add Transactions" into "Transfers" | Developer | Alex, James T | 5 |  | 2 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Implement more widgets into landing page | Developer | Alex, James T | 8 |  | 2 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Develop Demo for current iteration | Developer | Liz, Colin | 2 |  | 2 |  | 0 | 0 | 0 | 0 | 0 | 0
| Analysis |  |  |  |  | 9 |  | 9
|  | System Testing | Tester | Liz, Colin | 5 |  | 2 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Bug fix as required | Tester, Developer | Alex, James T | 2 |  | 2 |  | 0 | 0 | 0 | 0 | 0 | 0
|  | Evaluate needs for next iteration | Project Manager | Liz, Colin | 2 |  | 5 |  | 0 | 0 | 0 | 0 | 0 | 0
Total | [5 empty] | 186 |  | 131 | 17 | 16 | 10 | 10 | 15 | 14